## Slide 1: NEW STUDY PROGRAM IN SPACE SYSTEMS AND COMMUNICATIONS ENGINEERING (SPACECOM)

## Slide 2: NEW STUDY PROGRAM IN SPACE SYSTEMS AND COMMUNICATIONS ENGINEERING (SPACECOM) PROJECT DESCRIPTION
Khabibullo Nosirov, SPACECOM Project Coordinator
Tashkent University of Information Technologies named after Muhammad al-Khwarizmi, Uzbekistan

## Slide 3
Contents:
Consortium
Aims and objectives
Workplan
Description of work packages
Work breakdown structure
Project management structure
Contact list
Discussion

## Slide 4
The Consortium:
Tashkent University of Information Technologies,
Technical University of Berlin,
University of Sorbonna,
Artesis-Plantijn University of Applied Sciences,
Technical University of Sofia,
EXOLAUNCH,
Coursento,
National University of Uzbekistan,
Tashkent State Technical University,
Turin Polytechnic Institute in Tashkent,
Karshi branch of TUIT,
Ferghana Polytechnic Institute,
Branch center of retraining and professional development of pedagogical staff under TUIT,
Astronomical Institute of the Uzbek Academy of Sciences.

## Slide 5
The main objectives of the project are:
Development and modernization of the existing master's program in satellite technology, space technology and communication systems, as well as the use of satellite communications in accordance with the recommendations of the Bologna process.

## Slide 6
Expected Project Results:
- opening new master program in space engineering and technology has been opened;
- modernization of the existing and development of new courses related to Space and Communication Engineering;
- organizing new educational-scientific research laboratory for space engineering and technology;
- re-training personal of TUIT and its branches;
- developing new handbook and educational-methodological manuals.

## Slide 7: Partners
P1 - Tashkent University of Information Technologies
P2 - Technische Universität Berlin
P3 - Sorbonne Universite
P4 - Artesis-Plantijn University of Applied Sciences
P5 - Technical University Sofia
P6 - EXOLAUNCH
P7 - Coursento
P8 - Ferghana Polytechnical Institute
P9 - Tashkent State Technical University
P10 - Turin Polytechnic University in Tashkent
P11 - Karshi University of Information Technologies
P12 - National University of Uzbekistan
P13 - Astronomical Institute of the Uzbekistan Academy of Sciences
P14 - Retraining In-Service Center of Academic Staff

## Slide 9
WP1: Preparation
- To review, to analyse, to present analysis, to work out recommendations and to upgrade the existing curricula.
- Development of questionnaire for the need analysis – P4/P7;
- Setting up a framework for curricula – P1/P2/P6/P7;
- Development of guidelines for learning outcomes definition – P1/P2;
- Analysis of job needs P6/P13;
- Need analysis in UZ P1-P14;
- Need analysis in the EU – P2-P7;

## Slide 10
WP2 Development (Leading P2)
P1 – development of the syllabus and the content of the courses “Digital communications”
P2 – development of the syllabus and the content of the courses “Fundamentals of Space Technology”, “Satellite Technologies”, “Space system design”, “Satellite communication», «Applied Project Management for Space System», «Theory of Inventive Problem Solving», «Electronic Design and Assembly of communictions systems»
P3 – development of the syllabus and the content of the courses “Celestial mechanics for space mission engineering, Advanced Microelectronics: design of custom integrated circuits in CMOS technologies for space applications, Programming Principles & Object Oriented programming

## Slide 11
WP2 Development (Leading P2) cont.
by P6-practice oriented workshop. Then the responsible partners will at home work out the agreed curricula/modules to be adapted in target HEIs. Based on the new curricula/modules P1, P7 - P12 supported by P1-P5 will prepare/publish teaching materials. The leader of WP1 will be P2. Concerning WEB platform P1 and P2 will discuss with P7-P14 content of WEB platform and methodology of database creation. In 12.month of the second project year the new curricula/modules will be adopted on institutional level and in 9.month of the 3 project year accredit on national level. Equipment lists/lay out for GSLAB/SATLAB are the task of P1/P2/P6. The procedure of preparing purchase of the equipment is the task of P2/P6 in collaboration with target universities: choosing the sellers, working out shipping contracts, shipping timetable etc. Mile stones: new curricula/modules; handbooks published; new GSLAB/SATLAB platform. Performance indicators: number of curricula/modules developed/adopted/accredit; number of handbooks published; new GSLAB/SATLAB equipped on schedule. In the frames of intern evaluation all partners present a Monitoring report in each activity of WP2, as the link to overall coordination. Linkages with WP3-WP5 are foreseen.

## Slide 12
WP2 Development (Leading P2) cont.
P4 – development of the syllabus and the content of the courses “Development of space-grade embedded systems, Educational digital tools & blended learning tools for engineering education, Data protection,
P5 – development of the syllabus and the content of the courses “CAD tools for design of systems on chip” and “Microelectronics for Information and Communication technologies”
P6 – Workshop “Hot topics in satellite communication system using D-Star technology»
The partners will set up a Work Plan on WP2 inclusive timetable distributing the tasks of each participant to achieve the objectives. During the seminar at P1 in a special workshop on new curricula/module responsible partners will present the planned curricula/modules; the target HEIs and invited stakeholders will discuss and agree the content of curricula/modules to be developed by P1-P5 core curricula; by P2, P4 elective curricula

## Slide 13
WP3 Quality Plan (Leading org. P6)
Development of questionnaire for need analysis – P2/P7
Evaluation of the need analysis report – during the second project meeting, PMB
Peer review of syllabi – all, during the third project meeting
Development of questionnaire for usability tests of the e-learning environment and courses – P1/P6;
Design walkthrough of e-learning environment – course developers from all partner institutions;
Usability test – online by tutors and learners and during the fourth project meeting;
Peer review of e-learning courses – online, All partners;
Evaluation of learning attitudes to the innovated curricula – teachers and learners from all partner institutions during the pilot test and field trial;
QA of project activities and results – during all PMB meetings;
QA report – external evaluator.

## Slide 14
WP4 DISSEMINATION & EXPLOITATION (Leading org. P7)
Dissemination of related outputs /outcomes defined. Joint WEB based platform; establish C-Office with stakeholders, attraction of media awareness

## Slide 15
WP5 Management (Leading org. P1)
Local management and administration – All
All partners will be responsible for a workpackage or for a workgroup:
Leading the workgroup on need analysis – P1/P7;
Leading the workgroup on course development – P2;
Leading the workgroup on e-learning materials - P4;
Leading the workgroup on evaluation – P6;
Leading the workgroup on dissemination – P7.
WP1 leader: P4
WP2 leader: P2
WP3 leader: P6
WP4 leader: P7
WP5 leader: P1;
Organisation of kick-off meeting in Tashkent– P1
Sub-contracting external evaluator and auditors – P1
Organisation of PMB meetings for need analysis in UZ– P7
Organisation of PMB meeting for syllabi evaluation– P2, P3, P5
Organisation of training seminar for teachers – P1-P7
Organisation of PMB meeting for e-learning materials evaluation in Antwerp– P4
Organisation of PMB meeting for the pilot test in UZ – P9, P11, P13
Organisation of PMB meeting for the field trial evaluation and exploitation agreement in Sofia – P5
Organisation of final PMB meeting and dissemination workshop – P1, P2, P6, P9, P12, P14
Attendance of meeting of CBHE EA in Brussels – P1, P2
Intermediate and final reports – contact persons of all partner organisations and the project co-ordinator

## Slide 16
Thank You!
Khabibullo Nosirov, PhD
Project coordinator, Head of the Department
Tashkent University of Information Technologies named after Muhammad al-Khwarizmi
Radio and Mobile Communications Faculty
Amir Temur 108, 100084
Tashkent, Uzbekistan
n.khabibullo1990@gmail.com
+998 99 811 57 62 (WhatsApp)
+998 90 911 57 62 (Telegram)
www.tuit.uz (www.spacecom.uz)